FCA-E EMI Easy Reference Guide

THANK YOU for hosting an Endurance Ministry Institute! This document is intended to assist you in planning, make sure the important details are covered, and maximize the number of participants.
Directions: 
1.Once you decide the date of your event, fill in all the “_____ (date)” with applicable date  


2. Check off each “___” when task is complete.



3. Jot down ideas/comments/suggestions on last page as you have them.
Abbreviations used in this document:


EMI – Endurance Ministry Institute 

HLYG – Huddle Leaders’ Yahoo Group 


National – FCA Endurance National 

ND – National Director of FCA Endurance 


NYG – National Yahoo Group

Definitions: 


Conference – EMI event where people stay at in the local area (nominally Fri-Sat event)


Equipping Team Lead or Coordinator – person who is coordinating on behalf of FCA-E National


Host – Local contact who is coordinative logistics


Instructor(s) – all people who will be teaching classes


Retreat – EMI event where people stay in a common location (nominally Fri-Sun event)

Appendices:

Appendix A: Sample publicity statements for email (see also Appendix E)

Appendix B: Sample schedule - please coordinate all schedule changes with FCA-E Equipping Team  Lead
Appendix C: Sample “what to bring” list in 

Appendix D: Sample prayer request list in 

Appendix E: Sample press releases that have been used on National’s website. Feel free to modify/use.
Appendix F: Sample registration form (also available in Excel format from dlkohout@yahoo.com )

Appendix G: Template for building the Notebooks

Appendix H: Shopping list and Host’s “what to bring” list
____________________________________________________________________________________

 Initial Planning:  More than 6 months out
______________ (date)
___  Pick date:
 Consider/coordinate with
___ Local/state/etc. race/event schedule 







___ National Director / Equipping Team Lead







___ Instructor(s)







___ Nearby Huddles (as appropriate)







___ Invited guests1
___  Choose venue; Considerations: 

- room big enough to comfortably seat all participants at tables (6-8/table); 

- capability to project slides and videos from a computer onto a screen easily visible to all;

- childcare capability with appropriate facilities;

- ideally, location allows easy access but is far enough from “home” that once people arrive, they will stay for the entire program (retreat setting is preferable);

- ideally, easy access to running/riding/hiking with facilities to shower afterwards

___  Determine lodging options; consider homestays
___  Begin coordinating food/catering (menu (think “athletes: healthy!”),  provider, etc)
(1 Invited guests may include instructors in training, HL’s interested in hosting an event, etc)

____________________________________________________________________________________

 6 months out
______________ (date)
___  Reserve venue for conference time PLUS 3 hours before first event and 3 hours after last event
___  Complete details of food/catering 

___  Reserve lodging (if applicable)

___ Set up Active.com registration (if desired. Free of charge, easy, donation option available)


Include “Release and Waiver of Liability” – or – have these available at registration

___  Calculate cost:
(item

per person
# expected
total

)




Venue

$_______
__

$___________




Lodging
$_______
__

$___________



Food/snacks
$_______
__

$___________




Supplies
$    4.00   
__

$___________




Travel (ND)
$_______
__

$___________




   (instructors)
$_______
__

$___________




   (invited guests) $_______
__

$___________




Lodging (ND)
$_______
__

$___________




   (instructors)
$_______
__

$___________




   (invited guests) $_______
__

$___________




Misc

$_______
__

$___________




Grand Total




$___________




Divide by # expected



    ÷ _____




Total per person



$___________*
(*Consider offering discounts to early sign-ups and higher rates / late fee for later sign-ups. Must have minimum of 10 deposits (15 for a retreat-type event) before event will be considered a “go”.)
Publicity:

___  Craft catchy, short  invitation  including event, date, location, cost, reason why people should come2
___  Email:
___  FCA-E teammates/ministry partners in state/surrounding states (if appropriate)



___  Huddle Leaders

___  Post on:
___  NYG



___  HLYG
___ Post on Huddle website and/or EMI website
(2 some examples are available in the addendum to this document.)
____________________________________________________________________________________

 3 months out
______________ (date)
___ Finalize venue, lodging, food details – coordinate schedule as appropriate
___ Set/publicize registration deadline(s)

Publicity:

___  Phone call: 
___ ALL key people you’d like to invite

___  Invite via email:
___  FCA-E teammates/ministry partners in state/surrounding states (if appropriate)




___  Other local Christian organizations with whom you have contact
___  Post on:
___  NYG



___  HLYG
___ Update Huddle website and/or EMI website and/or National website
 1 month out
______________ (date)
___ Finalize schedule3 – coordinate with instructor(s), venue staff, food provider
___ Find 2 appropriately-sized bikes and bike trainers available at the event for the dramatic readings (skits)


Publicity:

___  Invite via email:
___  FCA-E teammates/ministry partners in state/surrounding states (if appropriate)




___  Individuals in other local Christian organizations you have contact with

___  Post on:
___  NYG



___  HLYG
___ Update Huddle website and/or EMI website and/or National website


Post “what to bring”4 list, maps/directions, schedule, etc.
(3Coordinate with FCA-E Equipping Team Lead – sample in Appendix B)

____________________________________________________________________________________ 
 1-2 weeks out
______________ (date)
___ Double check arrangements with venue, lodging, food providers

___ Email details / “what to bring” list4 / prayer request list5 to all participants and staff
___ Email prayer request list to Prayer Team (via National website or direct)
___ Update Huddle website and/or EMI website and/or National website

___ Purchase all items on the “shopping list” (Appendix H)
___ Print Witness Style Test, Critique Sheet, Schedule and One Word Evangelism (one per notebook)

___ Purchase, print and build notebooks – Please carefully follow notebook template,  Appendix G!
___ Print Ice Breaker slides (ONE slide per page)

___ Prepare nametags 
___ Print maps for outdoor activities (running, biking, etc., as required)

(4Sample “what to bring” list in Appendix C)

(5Sample prayer request list in Appendix D) 

Appendix A: Sample publicity statements
Change highlighted areas (and other wording and links) as necessary.

Sample 1: We cordially invite you to gain practical knowledge and training to use your athletic passion to introduce your friends to Jesus Christ. This is for athletes so you & your family will have time to work out & play!

Sample 2: FCA-E invites you to gain practical insights/skills to use your sports to introduce friends to Christ. It is for athletes so you & your family will have time to train & play!

Sample 3: Have you ever wondered how to more effectively share your relationship with Jesus Christ through your passion for running? If so, FCA Endurance in partnership with [church, other club, athletic group, YMCA, etc.] is offering you & your family the perfect opportunity.

Sample 4: FCA Endurance cordially invites you to gain practical knowledge and training in using your athletic passion to introduce your friends to Jesus Christ. This evangelism training retreat is tailored specifically for athletes, so you and your family will have plenty of time to work out and play!

Sample 5: Have you ever wondered how to more effectively share your faith through your passion for sports? If so, we have the perfect opportunity for you! The FCA-E Endurance Ministry Institute on [date] is tailored specifically for athletes, so you and your family will have plenty of time to work out and play! Click HERE to find out more, or register at active.com. 
Other items to consider including:

 - Rates / deadline for next rate increase

 - Registration information / link to registration website
 - Links to website(s) for more information

 - Location

Appendix B: Sample schedule for weekend retreat: 

**Please coordinate all schedule changes with instructor(s)**

         Friday 

1700-1800 
Check-in
1800-1900 
Dinner
1900-1945 
Weekend Overview
2000-2100
“Endurance sports outreach in the 21st Century” 



       - Demographics, the importance of relationships & proving that faith “works”
         Saturday

0700-0800 
Morning run/hike/etc.
0800-0830 
Shower
0830-0930 
Breakfast 
0930-1015 
“Christ’s story in your life” 



     - How to focus your testimony on Christ’s work in your life
1015-1030
Skit: Rolling Testimony 
1045-1130 
Testimony writing workshop 
1145-1230 
 “Divine appointment preparation” 



     - Overcoming fears, steering conversations, methods
1230-1330 
Lunch
1330-1415
“Are You Ready For This Race?” 


         - How to concisely, convincingly present the gospel

1415-1430
Skit: Drawing in the Dirt

1430-1700 
Afternoon ride/run
1700-1730 
Shower
1730-1830 
Dinner  
1830-1945 
Evangelism Methods Workshop 
2000-2045 
Basic Follow-up techniques

2045-2100
Skit: Life-Training
         Sunday

0700-0800 
Morning run/hike

0800-0830 
Shower
0830-0840 
Skit: The Upset

0840-0920 
Breakfast 
0930-1030 
Worship Service
1030-1130 
Pack up and check out

1130-1230 
Closing prayer and light Lunch 
Appendix B cont’d: Sample schedule for two-day conference, mid-day work-out: 

**Please coordinate all schedule changes with instructor(s)**

         Friday 

1800-1900 
Check-in
1900-1945 
Weekend Overview
2000-2100
“Endurance sports outreach in the 21st Century” 



       - Demographics, the importance of relationships & proving that faith “works”
         Saturday

0830-0915 
“Christ’s story in your life” 



     - How to focus your testimony on Christ’s work in your life
0915-0930
Skit: Rolling Testimony 
0945-1030 
Testimony writing workshop 
1045-1130 
 “Divine appointment preparation” 



     - Overcoming fears, steering conversations, methods
1130-1230 
Lunch
1230-1315 
“Are You Ready For This Race?” 


         - How to concisely, convincingly present the gospel

1315-1330
Skit: Drawing in the Dirt

1345-1430
Evangelism Methods Workshop

1430-1700 
Afternoon ride/run
1700-1730 
Shower
1730-1830 
Dinner

1830-1845 
Skit: The Upset
1845-1930
Evangelism Methods Workshop 
1945-2030 
Basic Follow-up techniques

2030-2045
Skit: Life-Training
2045-2100
Wrap-up
Appendix C: Sample “what to bring” list 
What to bring with you:
o  Bible

o  notebook

o  pen

o  linens for double bed or sleeping bag

o  pillow

o  alarm clock

o  toiletries

o  towel / shower shoes (flip-flops)

o  directions to [venue]
            (available on the “travel” page of the retreat website)

o  camping chair / blanket

o  jacket / cold  wx clothes

o  rain gear / umbrella

o  warm weather clothes

o  flashlight / batteries

o  camelback / water bottles

o  bike gear

o  bike

o  helmet

o  jersey / shorts / socks

o  cold / wet weather gear

o  shades

o  shoes

o  repair kit

o  gloves

o  _____________

o  _____________

o  running gear

o  shirt / shorts / socks

o  shades / hat

o  cold / wet weather gear

o  shoes

o  ______________

o  ______________

o  hiking gear

o  shirt / shorts / socks

o  shades / hat

o  cold / wet weather gear

o  hiking boots / shoes

o  ______________

o  ______________

Appendix D: Sample prayer request list
Change highlighted areas (and other wording and links) as necessary.

As the [retreat/conference] fast approaches, please join us in prayer for it. Please take a moment to pray for the following, now and each day this week:

· For smooth, complete, efficient preparation

· For safe, uneventful travel for all attendees to and from the retreat

· For preparation of the hearts and minds of all who will be attending

· That the enemy’s schemes would be thwarted 

· That God would be glorified 

Appendix E: Sample press releases
Change highlighted areas (and other wording and links) as necessary.

Sample 1:

“Hey.” a vaguely familiar voice draws your attention, “How come you’re not racing today?”

You’re volunteering at an event’s finish line, collecting timing chips. You recognize this racer because both of you ride with the local bike club. 

You look up from the timing chips and say. “Well, that’s a great question…”

You recognize the door the bike club rider opened. But do you have an answer ready (1 Peter 3:15)? And do you have the nerve to deliver it (Acts 9:27)?

In conjunction with Christian Runners.org, the Endurance in Faith and Sport Retreat, an evangelism training weekend, will address the fears involved in talking about faith. We’ll offer ideas to steer a conversation toward Jesus, and give you the chance to practice responding to an open door with the story that God has written in your own life. No one can argue with that story.

Available spots are dwindling, so sign up now at active.com. Find out more info on the retreat website.

Sample 2:

“Hey, you!” Rick shouts across the transition area. “Do you know Jesus?” His style of evangelism in definitely Direct! Mark, on the other hand, is fielding a question from a veteran triathlete he’s begun training with: “How do you know the Bible is true?” Mark feels his heart rate accelerate with excitement; he loves a good Intellectual challenge.

As she walks past Mark in the transition area, en route to her spot, Marcie deepens her relationship a tri newbie whom she helped earlier. She has listened carefully to the woman and is now gently but compellingly sharing her own Testimony. She waves to Frank as they pass him. He is talking with a young triathlete who was not openly hostile to him comment about competing in order to share his faith in Jesus. Frank Invites him to the pre-race prayer service at the next race in the series.

The underlined words are just a few Styles of Evangelism. It’s been said that it takes all kind of people to reach all kinds of people. Isn’t it amazing that God made us, with our specific style, in order to reach specific people who jive with who we are? 

Find out more about your style and how it can be most effectively used to impact your fellow athletes for eternity at the Evangelism Training Retreat on 27 Feb-1 Mar 2009 in South Carolina. Click HERE for more information, or HERE to register at active.com.

Sample 3:

“Hey, friend!” your co-worker bumps brashly by your desk on Friday afternoon. “What are you up to this weekend?” As you open your mouth to reply, you think, well, just church, but I don’t know if I should say that… As the interchange continues, you wonder why you hesitate to speak about your relationship with Jesus Christ. Could it be because you’ve simply never had the opportunity to practice bringing Him into everyday conversation?

Now you have that chance, combined with a weekend away in the mountains for the whole family! On Feb 27-Mar 1 at the Wesleyan Retreat Center next door to Table Rock State Park, FCA-Endurance is hosting an Endurance Ministry Institute designed to give you practical tools to help share your faith and hands-on practice using those tools. 

Sample 4:
The time has come! If you have been considering coming to the FCA-E Endurance Ministry Institute weekend in Greenville, SC, the time to commit is now. Registration will close on Feb 20. Don’t miss this unique opportunity to “train yourself for godliness”* even as you bask the beautiful, warm Table Rock State Park area and enjoy the fellowship of like-minded athletic brothers and sisters in Christ. 

Prices start at $125/person for food and lodging. Childcare provided. Find out more at www.donnadouglass.com/FCAE_training_retreat or sign up at active.com.

*1 Timothy 4:7-8

Appendix F: Sample registration form

[image: image1.emf]“Yes! Please save a spot for me at this retreat!”

Circle one:

Your name Phone H  C  W

Email address Phone H  C  W

Mailing address:

Names of those coming with you (one per line please) & ages of children under 12:

Name  Age

Name  Age

Name  Age

Name  Age

Name  Age

Desired accomodations 

(first choice and second choice please):

Room with two double beds Room with one double bed and two bunks

Room with 4 or 8 bunks RV spot with electric and water hook-ups

I would like to share a room with this person/couple:

(Please ensure that person/couple puts you on their registration form also!)

Ground transportation 

- check the appropriate boxes:

I'm local and will drive myself I can help drive people from the airport

I'm flying in and will rent a car I'm interested in carpooling from the airport

I'm a real endurance athlete and will ride my bike to the retreat

Other:

Activity preference for Saturday afternoon:

Check below if you're interested in leading this activity:

Run Desired distance:

Hike Desired distance:

Road Bike Desired distance:

Other:

Volunteering:

I/We can help with (check those that apply):

I'd like to help! Audio-video

My spouse said s/he would like to help! Registration

My teenage kids can help! Meal set-up/tear down

I volunteer _______________ to help! Greeting folks before meetings

Tear-down / clean up Sunday

General logistics

Childcare

Other: 

Cost:

(Please DO NOT write in the grayed-out areas. If the totals it is calucating are wrong, write us a note below.)

If you are sharing a room with another person/couple, enter here the number of people/couples splitting the cost:

Food: Sub-total:

Number of adults (12&up): $40.00 $0.00

Number of children (under 12): $20.00 $0.00

Number of rooms with 1 or 2 double beds: Lodging:

before/on 31 Dec 08: $120.00 $0.00

after 31 Dec 08: $150.00 $0.00

Number of bunks in bunk room:

before/on 31 Dec 08: $50.00 $0.00

after 31 Dec 08: $60.00 $0.00

RV hook-up (elec & water): $32.00 $0.00 Food and Lodging Sub-Total: $0.00 0

Drafting penalty (late fee $25) after 1 Feb 09 ("x" here):

Additional donation to FCA-Endurance (enter amount):

Grand Total: $0.00

Amount of deposit: Due no later than registration/check-in at the retreat: $0.00



EnduranceMinistry Institute

To Present the Gospel in the context of Endurance Sport


Appendix F: Notebook Template
Front pocket


- Critique sheet

Before first divider (in this order):


- Schedule


- Dramatic reading (skit) “resource sheet”


- One Word Evangelism article
Tab 1:


- Slides for Welcome presentation (printed 2 per page)

Tab 2:


- Slides for Endurance Sports Outreach presentation (printed 2 per page)

Tab 3:


- Slides for Christ’s Story presentation (printed 2 per page)

Tab 4:


- Slides for Testimony Writing Workshop presentation (printed 2 per page)

Tab 5:


- Slides for Divine Appointment Prep presentation (printed 2 per page)


- Witness Style Test (2 pages)

Tab 6:


- Slides for Are You Ready for This Race presentation (printed 2 per page)

Tab 7:


- Slides for Evangelism Workshop presentation (printed 2 per page)

Tab 8:


- Slides for Basic Follow-up Techniques presentation (printed 2 per page)

Appendix G: Shopping list
- Black or blue hard cover notebooks (one per participant, one per instructor)
- 1 package 3x5 cards

- Pens (one per participant, one per instructor)

- Poster hanging putty (like the like used in college dorm rooms – leaves wall and poster undamaged)

- Healthy snacks

- Water

- Coffee

- Other drinks

Host’s “what to bring” list
- All items on shopping list

- Applicable items on participant’s “what to bring” list

- Napkins, cups, utensils, etc.

- Notebooks

- Camera

- 2 bikes

- 2 trainers

- Music stand (if available, for Dramatic Reading)

- Name tags
8

_1302887599.xls
registration

		

		“Yes! Please save a spot for me at this retreat!”												Circle one:

		Your name								Phone				H  C  W

		Email address								Phone				H  C  W

		Mailing address:

		Names of those coming with you (one per line please) & ages of children under 12:

		Name								Age

		Name								Age

		Name								Age

		Name								Age

		Name								Age

		Desired accomodations (first choice and second choice please):

				Room with two double beds						Room with one double bed and two bunks

				Room with 4 or 8 bunks						RV spot with electric and water hook-ups

		I would like to share a room with this person/couple:

				(Please ensure that person/couple puts you on their registration form also!)

		Ground transportation - check the appropriate boxes:

				I'm local and will drive myself						I can help drive people from the airport

				I'm flying in and will rent a car						I'm interested in carpooling from the airport

				I'm a real endurance athlete and will ride my bike to the retreat

				Other:

		Activity preference for Saturday afternoon:								Check below if you're interested in leading this activity:

				Run		Desired distance:

				Hike		Desired distance:

				Road Bike		Desired distance:

				Other:

		Volunteering:								I/We can help with (check those that apply):

				I'd like to help!								Audio-video

				My spouse said s/he would like to help!								Registration

				My teenage kids can help!								Meal set-up/tear down

				I volunteer _______________ to help!								Greeting folks before meetings

												Tear-down / clean up Sunday

												General logistics

												Childcare

												Other:

		Cost:		(Please DO NOT write in the grayed-out areas. If the totals it is calucating are wrong, write us a note below.)

		If you are sharing a room with another person/couple, enter here the number of people/couples splitting the cost:

								Food:		Sub-total:

		Number of adults (12&up):						$40.00		$0.00

		Number of children (under 12):						$20.00		$0.00

		Number of rooms with 1 or 2 double beds:						Lodging:

				before/on 31 Dec 08:				$120.00		$0.00

				after 31 Dec 08:				$150.00		$0.00

		Number of bunks in bunk room:

				before/on 31 Dec 08:				$50.00		$0.00

				after 31 Dec 08:				$60.00		$0.00

		RV hook-up (elec & water):						$32.00		$0.00				Food and Lodging Sub-Total:		$0.00		0		25

		Drafting penalty (late fee $25) after 1 Feb 09 ("x" here):

		Additional donation to FCA-Endurance (enter amount):

														Grand Total:		$0.00

		Amount of deposit:												Due no later than registration/check-in at the retreat:		$0.00



Endurance Ministry Institute

To Present the Gospel in the context of Endurance Sport



qweep

		

		name tags

		maps		airport

				hiking

				biking

				running

				local attractions

		transportation coordination

		a/v support





Sheet3

		












